## Copyright
Copyright
# Planning-Template.xlsx Copyright (C) 2012-2026 Rafael Corchuelo. In keeping with the traditional purpose of furthering education and research, it is the policy of the copyright owner to permit non-commercial use and redistribution of this software. It has been tested carefully, but it is not guaranteed for any particular purposes. The copyright owner does not offer any warranties or representations, nor do they accept any liabilities with respect to them.
REVISAR EL NÚMERO DE ENTREGAS ESTE CURSO!!!!!
La columna estatus es redundante con Execution Period. Poner autocalculada.
Poner filtros en las columnas.

## Abstract
Abstract
This spreadsheet is intended to facilitate planning on the tasks of your project. Please, share it in your workgroup and closely follow the methodology taught.
Help comments
Enter configuration data in these cells
Warning and error messages.
Data computed automatically. Do not change them.
Internal data. Do not change them.

## D01
Deliverable D01
Use this form to document the tasks that you perform in your projects. Please, review the colour code in the "Abstract" sheet. In the exceptional case that you need to perform more tasks than expected, add them at the end.
| Costs | Expected: | 1152.5
|  | Actual: | 1322.5
[7 empty] | Execution period |  |  | Workload (in hours) |  | Costs (in EUR)
ORDER | ID | Type | Assignee | Role | Activity | Parent | Start moment | End moment | Status | Expected | Actual | Expected | Actual | Description
1 | T0001/M | Management | Student 2 | Manager | Initialise repository |  | 2026-02-08 10:30 | 2026-02-08 23:59 | Completed | 1 | 1 | 50 | 50 | Intialize repository
2 | T0002/D | Development | Student 2 | Developer | Customise the starter |  | 2026-02-08 10:30 | 2026-02-08 23:59 | Completed | 1 | 1 | 25 | 25 | Change information and images
3 | T0003/D | Development | ALL | Developer | Implement feature |  | 2026-02-08 10:30 | 2026-02-08 23:59 | Completed | 0.5 | 0.5 | 12.5 | 12.5 | Implement general model Validators
4 | T0004/D | Development | Student 2 | Tester | Check task |  | 2026-02-08 10:30 | 2026-02-08 23:59 | Completed | 0.5 | 0.25 | 15 | 7.5 | Check everything
5 | T0005/D | Development | Student 1 | Developer | Implement feature |  | 2026-02-16 10:30 | 2026-03-19 23:59 | Completed | 1 | 2 | 25 | 50 | S1/1
6 | T0006/D | Development | Student 1 | Developer | Implement feature |  | 2026-02-16 10:30 | 2026-03-19 23:59 | Completed | 4 | 3.25 | 100 | 81.25 | S1/2
7 | T0007/D | Development | Student 1 | Developer | Implement feature |  | 2026-02-16 10:30 | 2026-03-19 23:59 | Completed | 2 | 1 | 50 | 25 | S1/3
8 | T0008/D | Development | Student 1 | Developer | Implement feature |  | 2026-02-16 10:30 | 2026-03-19 23:59 | Completed | 4 | 5.5 | 100 | 137.5 | S1/4
9 | T0009/D | Development | Student 1 | Developer | Implement feature |  | 2026-02-16 10:30 | 2026-03-19 23:59 | Completed | 1 | 1 | 25 | 25 | S1/5
10 | T0010/D | Development | Student 1 | Developer | Implement feature |  | 2026-02-16 10:30 | 2026-03-19 23:59 | Completed | 3 | 5.5 | 75 | 137.5 | S1/6
11 | T0011/R/ | Revision | Student 1 | Tester | Check deliverable |  | 2026-03-16 10:30 | 2026-03-19 23:59 | Completed | 5 | 4 | 150 | 120 | Test the Student 1 features and check the deliverable
12 | T0012/D | Development | Student 2 | Developer | Implement feature |  | 2026-02-16 10:30 | 2026-03-19 23:59 | Completed | 1 | 2 | 25 | 50 | S2/1
13 | T0013/D | Development | Student 2 | Developer | Implement feature |  | 2026-02-16 10:30 | 2026-03-19 23:59 | Completed | 4 | 5.25 | 100 | 131.25 | S2/2
14 | T0014/D | Development | Student 2 | Developer | Implement feature |  | 2026-02-16 10:30 | 2026-03-19 23:59 | Completed | 2 | 1.5 | 50 | 37.5 | S2/3
15 | T0015/D | Development | Student 2 | Developer | Implement feature |  | 2026-02-16 10:30 | 2026-03-19 23:59 | Completed | 4 | 3.5 | 100 | 87.5 | S2/4
16 | T0016/D | Development | Student 2 | Developer | Implement feature |  | 2026-02-16 10:30 | 2026-03-19 23:59 | Completed | 1 | 1 | 25 | 25 | S2/5
17 | T0017/D | Development | Student 2 | Developer | Implement feature |  | 2026-02-16 10:30 | 2026-03-19 23:59 | Completed | 3 | 5 | 75 | 125 | S2/6
18 | T0018/R/ | Revision | Student 2 | Tester | Check deliverable |  | 2026-03-16 10:30 | 2026-03-19 23:59 | Completed | 5 | 6.5 | 150 | 195 | Test the Student 2 features and check the deliverable
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## D02
Deliverable D02
Use this form to document the tasks that you perform in your projects. Please, review the colour code in the "Abstract" sheet. In the exceptional case that you need to perform more tasks than expected, add them at the end.
| Costs | Expected: | 0
|  | Actual: | 0
[7 empty] | Execution period |  |  | Workload (in hours) |  | Costs (in EUR)
ORDER | ID | Type | Assignee | Role | Activity | Parent | Start moment | End moment | Status | Expected | Actual | Expected | Actual | Description
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## D03
Deliverable D03
Use this form to document the tasks that you perform in your projects. Please, review the colour code in the "Abstract" sheet. In the exceptional case that you need to perform more tasks than expected, add them at the end.
| Costs | Expected: | 0
|  | Actual: | 0
[7 empty] | Execution period |  |  | Workload (in hours) |  | Costs (in EUR)
ORDER | ID | Type | Assignee | Role | Activity | Parent | Start moment | End moment | Status | Expected | Actual | Expected | Actual | Description
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## Internal
Internal data
This sheet contains internal data that are used elsewhere to perform some checks and computations. Please, do not modify it al all.
Prospective assignees
Student 1
Student 2
Student 3
Student 4
Student 5
ALL
Statuses
Planned
Ongoing
Finished
Moments
2025-01-01
2100/31/12 23:59:59
Roles | Cost | Tasks…
Student | 0 | Attend lecture | Study and train | Attend work meeting | Other (Describe)
Manager | 50 | Make plans | Make re-plannings | Initialise repository | Supervise task | Write report | Other (Describe)
Analyst | 40 | Elicit requirements | Define features | Create domain model | Write report | Other (Describe)
Developer | 25 | Create dev. config. | Customise the starter | Implement feature | Test feature informally | Write report | Other (Describe)
Tester | 30 | Check deliverable | Check task | Test feature formally | Test performance formally | Write report | Other (Describe)
Operator | 30 | Prepare dep. platf. | Package deliverable | Upload deliverable | Deploy application | Keep application running | Write report | Other (Describe)
Other | 10 | Other (Describe)
Task types | Key
Management | M
Development | D
QA | QA
Revision | R
Other | O